## Slide 1: Construction of Activity-On-Node (AON) PERT Diagram from Project Schedule

## Slide 2: Characteristics of Activity-On-Node (AON) PERT Diagram
Maybe more than one single start and end node.
Nodes represent activities.
Arrows indicate precedence.
Example:
Activity | Predecessor
A | None
B | None
C | A
D | B, C
E | D
A
B
C
D
E

## Slide 3: Activity-On-Node (AON) PERT Diagram Example
A
Activity | Predecessor
A | None
B | A
C | A
D | B, C
E | D
B
C
D
E

## Slide 4: Activity-On-Node (AON) PERT Diagram Example
A
Activity | Predecessor
A | None
B | None
C | None
D | A, B
E | B
F | B, C
B
C
D
E
F

## Slide 5: Activity-On-Node (AON) PERT Diagram Example
B
Activity | Predecessor
A | None
B | A
C | A
D | B
E | C
F | D, E
A
C
D
E
F

## Slide 6: Activity-On-Node (AON) PERT Diagram Example
B
Activity | Predecessor
A | None
B | A
C | A
D | B
E | B, C
F | C
G | D, E, F
A
C
D
E
F
G

## Slide 7: Activity-On-Node (AON) PERT Diagram Example
A
C
D
B
E
G
F
H
I